## Checklist
Days | Action | Yes/No | Responsible | Accountable | Informed | Consulted | Checklist | Yes/No
-120 | Venues identified |  | Sales Leader | Trainer | Sales Angel | Sales Leader | Meet Venue recce criteria
-90 | Contract agreed with venue |  | Sales Angel, Sales Leader, Trainer | Sales Leader | Sales Angel, Trainer | Trainer | Min guarantee agreed
Timings agreed
Extra time agreed, if needed
Max hall capacity known
All agreements documented by e-mail
Contract approved by Trainer
For new venues the following is checked
Menu with 1 non spicey and 1 green vegetable/porial type (no potato agreed)
Sofa availability
2 rectangle tables with ironed cloth in the back of the room (for sound desk)
Water/Water bottles
Tissues
Flip Chart Paper, Whiteborad and Easel
Pen & Paper
Stage options
Light options
-89 | Venue What's App Filled in |  | Sales Leader | Sales Angel | Trainer | Sales Leader | Filled in template posted on What's App Event group
-85 | Website page checked |  | Sales Leader | Sales Angel | Trainer | Sales Leader | Dates, poster, pricing, offers, location, google map, booking links
| E-mail's completed |  | Sales Leader | Sales Angel | Trainer | Sales Leader | Dates, poster, pricing, offers, location, google map, booking links
Initial E-mail Delegates
Confirmation E-mail Delegates
Final Confirmation E-mail Delegates
Follow Up E-mail
Confirmation E-mail Assist Team
Final Confirmation E-mail Assist Team
-80 | What's app messages completed |  | Sales Leader | Sales Angel | Trainer | Sales Leader | Dates, poster, pricing, offers, location, google map, booking links
Initial promo message with poster delegate
Confirmation message delegate
Final Confirmation Message delegate
Confirmation message assist team
Final Confirmation message assist team
Follow up message
-60 | Event listed on key sites |  | Sales Leader | Sales Angel | Trainer | Sales Leader | Journey Website
AAMET site
ANLP site
Mera events
-20 | Checklist reviewed |  | Sales Leader | Sales Angel | Trainer | Sales Leader | TBD
| Inventory reviewed | [5 empty] | TBD
| Shopping identified | [5 empty] | Decide on-line versus shop on the day
| Shipment organised | [5 empty] | Identify who will ship what when with budget agreed
-14 | Ask trainer assist team roles and timings |  | Sales Leader | Sales Angel | Trainer | Sales Leader
| Go through inventory requirements |  | Sales Leader | Sales Angel | Trainer | Sales Leader
-10 | Send running order and menu to venue |  | Sales Leader | Sales Angel | Trainer | Sales Leader
-10 | Approve follow up email, whats app and final confirmation e-mail and message for assist team |  | Sales Leader | Sales Angel | Trainer | Sales Leader
-9 | Speak to venue and check they have received everything and confirm all requirements will be provided |  | Sales Leader | Sales Angel | Trainer | Sales Leader
-8 | Finalise the Assist Roles and Assist Team timings |  | Sales Leader | Sales Angel | Trainer | Sales Leader
| Send all printing to printer with rates and delivery agreed |  | Sales Leader | Sales Angel | Trainer | Sales Leader
| Post latest confirmed delegate and assist team list on what’s app with high tentative list of those who are due to close |  | Sales Leader | Sales Angel | Trainer | Sales Leader
-7 | Send confirmation email to delegates and assist |  | Sales Leader | Sales Angel | Trainer | Sales Leader
| Confirmation calls prioritising those who have to make payment |  | Sales Leader | Sales Angel | Trainer | Sales Leader
-4 | Make certificates |  | Admin Officer | Sales Angel | Trainer | Sales Leader
-3 | Send what’s app confirmation |  | Sales Leader | Sales Angel | Trainer | Sales Leader
| Set up ASSIST team whats app group - welcome them and post the assist team information |  | Sales Leader | Sales Angel | Trainer | Sales Leader
| Check in with venue and update on numbers |  | Sales Leader | Sales Angel | Trainer | Sales Leader
| Set up group for VLC Contact, Trainer & on-site registration person what's app group |  | Sales Leader | Sales Angel | Trainer | Sales Leader
-2 | Get final set up time from venue |  | Sales Leader | Sales Angel | Trainer | Sales Leader | Announce time on group and agree with trainer
-1 | Send (by 11am) send final delegate and assist team whats app list with information on payments and registration form (green tick and red cross) |  | Sales Leader | Sales Angel | Trainer | Sales Leader | Add in the list and alert to the trainer - 1. Special diet 2. Special Needs - If they have any medical label 3. Birthdays
| Check in with venue on numbers and arrangements - provide and catering special needs by email |  | Sales Leader | Sales Angel | Trainer | Sales Leader
| Make the delegate lists and handover for printing |  | Sales Leader | Sales Angel | Trainer | Sales Leader | Catering, special needs and birthdays
Payments and balance
Registration info needed
Info for trainer on reasons
List for delegates to sign and confirm name, address and certificate name
0 | Event - make name badges, envelopes and identify any registration form info needed |  | Sales Leader | Sales Angel | Trainer | Sales Leader
0 | Event - set up broadcast list |  | Sales Leader | Sales Angel | Trainer | Sales Leader
0 | Flowers organised and purchased |  | Sales Leader | Sales Angel | Trainer | Sales Leader
0 | Printing delivered to venue |  | Sales Leader | Sales Angel | Trainer | Sales Leader
1 | Get payment and registration information from those who completed the registration process on site and update the what’s app list and bookings |  | Sales Leader | Sales Angel | Trainer | Sales Leader
| Post on registration group and event lead whats app group update on payments received, post photo of signed delegate list with certificate names and any registration forms |  | Sales Leader | Sales Angel | Trainer | Sales Leader
| Post photos of cheques handed over on event what’s app lead group to trainer and summary of cash amounts and get trainer to confirm all has been received in full by the close of the seminar |  | Sales Leader | Sales Angel | Trainer | Sales Leader
| Start documenting any cash bills and keep any bank transfer bills in folder to handover |  | Sales Leader | Sales Angel | Trainer | Sales Leader
| Send certificate for printing after confirming names |  | Sales Leader | Sales Angel | Trainer | Sales Leader
Last Day | Confirm numbers per day with venue and get final bill for payment and get payment completed via trainer |  | Sales Leader | Sales Angel | Trainer | Sales Leader
| Provide details of who commission is due and when with bank details to trainer |  | Sales Leader | Sales Angel | Trainer | Sales Leader
| Send what’s app message/sms to all that were lost or had to cancelled |  | Sales Leader | Sales Angel | Trainer | Sales Leader
| Send follow up email and what’s app message by 6pm |  | Sales Leader | Sales Angel | Trainer | Sales Leader | Saved send e-mail with Bcc in templates
| Document bills in excel and handover to trainer or post pictures of bills on “Bills” group for Akshu to document and check the excel print out and staple receipts and handover to trainer by Day 7 post seminar |  | Sales Leader | Sales Angel | Trainer | Sales Leader
| Collect comments sheets and post on registration group, event lead group and team leads for Akshu |  | Sales Leader | Sales Angel | Trainer | Sales Leader
| Post photographs on whats app group and on Facebook Vitality Living College in a album and share on trainer timeline tagging all team members |  | Sales Leader | Sales Angel | Trainer | Sales Leader
| Complete inventory checklist of all items leaving the event and if any shopping is needed |  | Sales Leader | Sales Angel | Trainer | Sales Leader
| Create what’s app group of delegates and welcome them |  | Sales Leader | Sales Angel | Trainer | Sales Leader
| Send message to those who cancelled, could not make it or book - get them into nuture.. |  | Sales Leader | Sales Angel | Trainer | Sales Leader
+1 | Read comments sheets and lead requests - identify comments for website and also improvement points for venue, trainer and team |  | Sales Leader | Sales Angel | Trainer | Sales Leader
| Collate any leads from the seminar for next seminar and add to appropriate lead lists |  | Sales Leader | Sales Angel | Trainer | Sales Leader
| Start posting daily what’s app message on the group |  | Sales Leader | Sales Angel | Trainer | Sales Leader
| Confirm all e-mail's saved in templates in venue, correspondance and printing |  | Sales Leader | Sales Angel | Trainer | Sales Leader
+2 | Review bookings and mark the following actions: payments pending and leads for next seminar |  | Sales Leader | Sales Angel | Trainer | Sales Leader
| Mark in calendar the follow up on payments |  | Sales Leader | Sales Angel | Trainer | Sales Leader
Post pending payments on group with dates
Post future leads on what's app group
| Post learnings from event on group |  | Sales Leader | Sales Angel | Trainer | Sales Leader | What worked well, what good be better and leanrings
+3 | Close bookings and announce its closed on the group |  | Sales Leader | Sales Angel | Trainer | Sales Leader
| Bookings moved to main database |  | Sales Admin | Sales Angel | Trainer | Sales Leader
Future Leads moved to next event
| What's App VLC Grad list and Event Grad List updated on phone ending on 625 |  | Sales Leader | Sales Angel | Trainer | Sales Leader
| De-brief with trainer completed |  | Sales Leader | Sales Angel | Trainer | Sales Leader
Vitality Living College™ - Empowering Transformation. ©2020 Rangana Rupavi Choudhuri, www.vitalitylivingcollege.info. All Rights Reserved. Do not share, copy, reproduce or sell any part of this document, it is known as theft, unless you have written permission from www.vitalitylivingcollege.info. All infringements will be prosecuted.